## Project_Plan
※Group Discussion will be every Monday morning at 7:00 CET / 15:00 JST. |  |  |  |  | Start Date | 2022-03-16 | End Date | 2022-05-10
[5 empty] | Year | 2022 | Month | 5
|  |  | Assignment Submission | [7 empty] | Planning Date | [5 empty] | Actual Completion Date | [5 empty] | Peer Review Date
[5 empty] | Planning Date |  | Actual Completion Date |  | Peer Review |  | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Members | * | Pending
| Week | Phase | Task | Assigned | Start Date | End Date | Start Date | End Date | Reviewer | Date Confirmed | 2022-05-01 | 2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05 | 2022-05-06 | 2022-05-07 | 2022-05-08 | 2022-05-09 | 2022-05-10 | 2022-05-11 | 2022-05-12 | 2022-05-13 | 2022-05-14 | 2022-05-15 | 2022-05-16 | 2022-05-17 | 2022-05-18 | 2022-05-19 | 2022-05-20 | 2022-05-21 | 2022-05-22 | 2022-05-23 | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-27 | 2022-05-28 | 2022-05-29 | 2022-05-30 | 2022-05-31 | Linden Crandall
| Week 1 | Preparation | Form Group | Linden Crandall | 2022-03-16 | 2022-03-22 | 2022-03-15 | 2022-03-16 | Zhihua Zheng | 2022-03-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Jonathan Mainhart
|  |  |  | Jonathan Mainhart | 2022-03-16 | 2022-03-22 | 2022-03-15 | 2022-03-16 | Zhihua Zheng | 2022-03-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Zhihua Zheng
|  |  |  | Zhihua Zheng | 2022-03-16 | 2022-03-22 | 2022-03-15 | 2022-03-16 | Zhihua Zheng | 2022-03-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Week 2 | Design | User Stories | Linden Crandall | 2022-03-22 | 2022-03-24 | 2022-03-22 | 2022-03-23 | Zhihua Zheng | 2022-03-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | User Stories | Jonathan Mainhart | 2022-03-22 | 2022-03-24 | 2022-03-22 | 2022-03-22 | Zhihua Zheng | 2022-03-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | User Stories | Zhihua Zheng | 2022-03-22 | 2022-03-24 | 2022-03-22 | 2022-03-23 | Jonathan Mainhart | 2022-03-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Week2 Discussion | Zhihua Zheng | 2022-03-23 | 2022-03-25 | 2022-03-23 | 2022-03-23 | Jonathan Mainhart | 2022-03-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Group Discussion |  | 2022-03-28 | 2022-03-28 | 2022-03-28 | 2022-03-28 | Zhihua Zheng | 2022-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Project Proposal | Linden Crandall | 2022-03-23 | 2022-03-29 |  |  | Linden Crandall | 2022-03-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Jonathan Mainhart | 2022-03-23 | 2022-03-29 | 2022-03-19 | 2022-04-21 | Jonathan Mainhart | 2022-03-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Zhihua Zheng | 2022-03-23 | 2022-03-29 | 2022-03-19 | 2022-03-25 | Jonathan Mainhart | 2022-03-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Week 3 |  | GUI Test Plan | Zhihua Zheng | 2022-03-30 | 2022-04-01 | 2022-03-28 | 2022-03-29 | Jonathan Mainhart | 2022-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Reset Test Plan | Zhihua Zheng | 2022-03-30 | 2022-04-01 | 2022-03-28 | 2022-03-29 | Linden Crandall | 2022-03-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Encode Test Plan | Jonathan Mainhart | 2022-03-30 | 2022-04-01 | 2022-03-23 | 2022-03-24 | Zhihua Zheng | 2022-03-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Decode Test Plan | Jonathan Mainhart | 2022-03-30 | 2022-04-01 | 2022-03-23 | 2022-03-24 | Zhihua Zheng | 2022-03-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | File I/O (Open/Save Image) | Linden Crandall | 2022-03-30 | 2022-04-01 | 2022-03-24 | 2022-03-29 | Jonathan Mainhart | 2022-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Integration Test Plan | Zhihua Zheng | 2022-03-30 | 2022-04-01 | 2022-03-29 | 2022-03-29 | Linden Crandall | 2022-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | User Guide | Linden Crandall | 2022-03-30 | 2022-04-01 | 2022-03-24 | 2022-03-31 | Jonathan Mainhart | 2022-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Week3 Discussion | Linden Crandall | 2022-03-30 | 2022-04-01 | 2022-04-01 | 2022-04-01 | Jonathan Mainhart | 2022-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Group Discussion |  | 2022-04-04 | 2022-04-04 | 2022-04-04 | 2022-04-04 | Zhihua Zheng | 2022-04-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Test Plan Draft | Zhihua Zheng | 2022-03-30 | 2022-04-04 | 2022-03-31 | 2022-03-31 | Linden Crandall | 2022-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Test Plan | Zhihua Zheng | 2022-03-30 | 2022-04-05 | 2022-03-31 | 2022-03-31 | Jonathan Mainhart | 2022-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Week 4 |  | Data Structure & Field | Jonathan Mainhart | 2022-04-06 | 2022-04-07 | 2022-04-05 | 2022-04-07 | Zhihua Zheng | 2022-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | GUI Design | Zhihua Zheng | 2022-04-06 | 2022-04-07 | 2022-04-05 | 2022-04-07 | Jonathan Mainhart | 2022-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | File I/O (Open & Save) | Linden Crandall | 2022-04-06 | 2022-04-07 | 2022-04-05 | 2022-04-07 | Jonathan Mainhart | 2022-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Encode a Text Message | Jonathan Mainhart | 2022-04-06 | 2022-04-07 | 2022-04-05 | 2022-04-07 | Zhihua Zheng | 2022-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Decode the Image | Jonathan Mainhart | 2022-04-06 | 2022-04-07 | 2022-04-05 | 2022-04-07 | Zhihua Zheng | 2022-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Reset the Image | Zhihua Zheng | 2022-04-06 | 2022-04-07 | 2022-04-05 | 2022-04-07 | Jonathan Mainhart | 2022-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Error handler Dialog | Zhihua Zheng | 2022-04-06 | 2022-04-07 | 2022-04-05 | 2022-04-07 | Jonathan Mainhart | 2022-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Week4 Discussion | Jonathan Mainhart | 2022-04-06 | 2022-04-08 | 2022-04-08 | 2022-04-08 | Zhihua Zheng | 2022-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Group Discussion |  | 2022-04-11 | 2022-04-11 | 2022-04-11 | 2022-04-11 | Zhihua Zheng | 2022-04-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Project Design Draft | Jonathan Mainhart | 2022-04-06 | 2022-04-11 | 2022-04-05 | 2022-04-08 | Linden Crandall | 2022-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Project Design | Jonathan Mainhart | 2022-04-06 | 2022-04-12 | 2022-04-05 | 2022-04-08 | Zhihua Zheng | 2022-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Week 5 | Implementation | dialog.kv - Popup Dialog | Zhihua Zheng | 2022-04-12 | 2022-04-14 | 2022-04-11 | 2022-04-14 | Jonathan Mainhart | 2022-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | stego.py - popup_user_notification() | Zhihua Zheng | 2022-04-12 | 2022-04-14 | 2022-04-11 | 2022-04-14 | Jonathan Mainhart | 2022-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | stego.py - class FileChooserPopup | Linden Crandall | 2022-04-12 | 2022-04-14 | 2022-04-11 | 2022-04-14 | Zhihua Zheng | 2022-04-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | mainframe.kv - <FileChooserPopup> | Linden Crandall | 2022-04-12 | 2022-04-14 | 2022-04-11 | 2022-04-14 | Zhihua Zheng | 2022-04-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | utils.py - convert_message() | Jonathan Mainhart | 2022-04-12 | 2022-04-14 | 2022-04-11 | 2022-04-14 | Zhihua Zheng | 2022-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Week5 Discussion | Zhihua Zheng | 2022-04-13 | 2022-04-15 | 2022-04-14 | 2022-04-15 | Jonathan Mainhart | 2022-04-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Group Discussion |  | 2022-04-18 | 2022-04-18 | 2022-04-18 | 2022-04-18 | Zhihua Zheng | 2022-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Phase 1 Source | Zhihua Zheng | 2022-04-13 | 2022-04-15 | 2022-04-14 | 2022-04-15 | Jonathan Mainhart | 2022-04-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Week 6 |  | mainframe.kv - complete class | Zhihua Zheng | 2022-04-19 | 2022-04-21 | 2022-04-19 | 2022-04-25 | Jonathan Mainhart | 2022-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | stego.py - complete class | Zhihua Zheng | 2022-04-19 | 2022-04-21 | 2022-04-19 | 2022-04-25 | Jonathan Mainhart | 2022-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | models.py - __init()__ | Jonathan Mainhart | 2022-04-19 | 2022-04-21 | 2022-04-11 | 2022-04-14 | Zhihua Zheng | 2022-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | models.py - encode_image() | Jonathan Mainhart | 2022-04-19 | 2022-04-21 | 2022-04-11 | 2022-04-21 | Zhihua Zheng | 2022-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | models.py - decode_image() | Jonathan Mainhart | 2022-04-19 | 2022-04-21 | 2022-04-11 | 2022-04-21 | Zhihua Zheng | 2022-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | models.py - reset_image() | Jonathan Mainhart | 2022-04-19 | 2022-04-21 | 2022-04-11 | 2022-04-14 | Zhihua Zheng | 2022-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | models.py - _extract_pixel_data() | Jonathan Mainhart | 2022-04-19 | 2022-04-21 | 2022-04-11 | 2022-04-21 | Zhihua Zheng | 2022-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | models.py - _calculate_max_chars() | Jonathan Mainhart | 2022-04-19 | 2022-04-21 | 2022-04-11 | 2022-04-21 | Zhihua Zheng | 2022-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | utils.py - save_image() | Linden Crandall | 2022-04-19 | 2022-04-21 | 2022-04-19 | 2022-04-21 | Zhihua Zheng | 2022-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Week6 Discussion | Linden Crandall | 2022-04-20 | 2022-04-22 | 2022-04-21 | 2022-04-21 | Zhihua Zheng | 2022-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Group Discussion |  | 2022-04-25 | 2022-04-25 | 2022-04-25 | 2022-04-25 | Zhihua Zheng | 2022-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Phase 2 Source | Linden Crandall | 2022-04-20 | 2022-04-26 | 2022-04-21 | 2022-04-21 | Zhihua Zheng | 2022-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Week 7 | Test | Update Test Cases - Unit Test | Zhihua Zheng | 2022-04-27 | 2022-04-29 | 2022-04-25 | 2022-04-27 | Jonathan Mainhart | 2022-04-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Update Test Cases - Unit Test | Jonathan Mainhart | 2022-04-27 | 2022-04-29 | 2022-04-25 | 2022-04-27 | Zhihua Zheng | 2022-04-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Update Test Cases - Manuel | Zhihua Zheng | 2022-04-27 | 2022-04-29 | 2022-04-25 | 2022-04-27 | Jonathan Mainhart | 2022-04-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Update Test Cases - Manuel | Jonathan Mainhart | 2022-04-27 | 2022-04-29 | 2022-04-25 | 2022-04-27 | Zhihua Zheng | 2022-04-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Test - Manuel | Linden Crandall | 2022-04-27 | 2022-04-29 | 2022-04-29 | 2022-04-29 | Jonathan Mainhart | 2022-04-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Test - Manuel | Zhihua Zheng | 2022-04-27 | 2022-04-29 | 2022-04-28 | 2022-04-28 | Jonathan Mainhart | 2022-04-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Test - Manuel | Jonathan Mainhart | 2022-04-27 | 2022-04-29 | 2022-04-28 | 2022-04-28 | Zhihua Zheng | 2022-04-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Unit Test - stego.py | Zhihua Zheng | 2022-04-25 | 2022-04-26 | 2022-04-25 | 2022-04-27 | Jonathan Mainhart | 2022-04-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Unit Test - models.py | Jonathan Mainhart | 2022-04-25 | 2022-04-26 | 2022-04-18 | 2022-04-21 | Zhihua Zheng | 2022-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Unit Test - utils.py | Jonathan Mainhart | 2022-04-25 | 2022-04-26 | 2022-04-18 | 2022-04-21 | Zhihua Zheng | 2022-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Week7 Discussion | Jonathan Mainhart | 2022-04-27 | 2022-04-29 | 2022-04-28 | 2022-04-29 | Zhihua Zheng | 2022-04-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Group Discussion |  | 2022-05-02 | 2022-05-02 | 2022-05-02 | 2022-05-02 | Zhihua Zheng | 2022-05-02 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Phase 3 Source | Jonathan Mainhart | 2022-04-27 | 2022-04-29 | 2022-04-28 | 2022-04-29 | Zhihua Zheng | 2022-04-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Week 8 | Final Review | Documents Revision | Linden Crandall | 2022-05-02 | 2022-05-04 | 2022-05-02 | 2022-05-04 | Jonathan Mainhart | 2022-05-03 | 0 | 2 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Documents Revision | Jonathan Mainhart | 2022-05-02 | 2022-05-04 | 2022-05-02 | 2022-05-04 | Zhihua Zheng | 2022-05-03 | 0 | 2 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Documents Revision | Zhihua Zheng | 2022-05-02 | 2022-05-04 | 2022-05-02 | 2022-05-02 | Jonathan Mainhart | 2022-05-03 | 0 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Final Report Input | Linden Crandall | 2022-05-02 | 2022-05-03 | 2022-05-02 | 2022-05-02 | Jonathan Mainhart | 2022-05-04 | 0 | 2 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Final Report Input | Jonathan Mainhart | 2022-05-02 | 2022-05-03 | 2022-05-03 | 2022-05-03 | Linden Crandall | 2022-05-03 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Final Report Input | Zhihua Zheng | 2022-05-02 | 2022-05-03 | 2022-05-02 | 2022-05-03 | Jonathan Mainhart | 2022-05-03 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Final Report Wrap Up | Jonathan Mainhart | 2022-05-03 | 2022-05-04 | 2022-05-03 | 2022-05-03 | Zhihua Zheng | 2022-05-03 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Final Submission Review | Linden Crandall | 2022-05-04 | 2022-05-04 | 2022-05-04 | 2022-05-04 | Linden Crandall | 2022-05-04 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Final Submission Review | Jonathan Mainhart | 2022-05-04 | 2022-05-04 | 2022-05-03 | 2022-05-03 | Jonathan Mainhart | 2022-05-03 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Final Submission Review | Zhihua Zheng | 2022-05-04 | 2022-05-04 | 2022-05-03 | 2022-05-03 | Zhihua Zheng | 2022-05-03 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Week8 Discussion | Zhihua Zheng | 2022-05-04 | 2022-05-06 | 2022-05-04 | 2022-05-04 | Linden Crandall | 2022-05-04 | 0 | 0 | 0 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Final Assignment | Zhihua Zheng | 2022-05-04 | 2022-05-06 | 2022-05-04 | 2022-05-04 | Jonathan Mainhart | 2022-05-04 | 0 | 0 | 0 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0